## Project Settings
/Proyecto/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Kevin Ray Marzola Otero
Start Date | abr 16, 2017 09:34:39 AM
Completion Date | abr 18, 2017 06:06:41 AM | Completed: *
Keywords
Language | Java
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:19 PM el 18/04/2017

## Overall Metrics
/Proyecto/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 35.6 | 28.2 | 35.5
Planned Time | 0.14097 |  | 1899-12-31 11:24
Actual Tiempo |  | 0.14653 | 1899-12-31 07:57
CPI (Cost-Performance Index) |  |  | 1.11
% Reuse | 42.5% | 48.1% | 17.5%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 3.87 | 0 | 3.53
Total Defects/KLOC or equivalent | 18.4 | 10.1 | 17.7
Yield % | 100% | 100% | 100%
Code Review Rate | 568 | 457 | 566
% Appraisal COQ | 14% | 15.6% | 14.1%
% Failure COQ | 7.97% | 6.16% | 7.77%
COQ A/F Ratio | 1.75 | 2.54 | 1.82
PQI | 0.14 | 0.64 | 0.17
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:21 PM el 18/04/2017

## Program Size
/Proyecto/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 137 | 144 | 696
Deleted (D) | 7 | 11 | 77
Modified (M) | 18 | 17 | 64
Added (A) | 103 | 82 | 1069
Reused (R) | 172 | 199 | 311
Added and Modified (A+M) | 121 | 99 | 1133
Total Size (T) | 405 | 414 | 1779
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 143 | 88 | 934
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:21 PM el 18/04/2017

## Time In Phase
/Proyecto/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.031944 | 0.041667 | 0.31042 | 23.3%
DiseÃ±o | 0.017361 | 0.029861 | 0.17431 | 13.1%
RevisiÃ³n de DiseÃ±o | 0.011111 | 0.013889 | 0.10486 | 7.88%
CodificaciÃ³n | 0.046528 | 0.026389 | 0.41458 | 31.1%
RevisiÃ³n de CodificaciÃ³n | 0.0090278 | 0.0090278 | 0.083333 | 6.26%
CompilaciÃ³n | 0.0034722 | 0.0020833 | 0.032639 | 2.45%
Pruebas | 0.0076389 | 0.0069444 | 0.070833 | 5.32%
Postmortem | 0.014583 | 0.016667 | 0.14028 | 10.5%
Total | 0.14097 | 0.14653 | 1899-12-31 07:57
Total Time UPI (70%) | N/A
Total Time LPI (70%) | N/A
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:22 PM el 18/04/2017

## Defects Injected
/Proyecto/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0.23 | 0 | 2 | 10%
DiseÃ±o | 1.05 | 1 | 10 | 50%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 0.47 | 0 | 4 | 20%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0.47 | 0 | 4 | 20%
Total | 2.22 | 1 | 20
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:22 PM el 18/04/2017

## Defects Removed
/Proyecto/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.23 | 0 | 2 | 10%
DiseÃ±o | 0.23 | 0 | 2 | 10%
RevisiÃ³n de DiseÃ±o | 0.47 | 1 | 5 | 25%
CodificaciÃ³n | 0.35 | 0 | 3 | 15%
RevisiÃ³n de CodificaciÃ³n | 0.47 | 0 | 4 | 20%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0.47 | 0 | 4 | 20%
Total | 2.22 | 1 | 20
After Development | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:23 PM el 18/04/2017

## Defect Removal Efficiency
/Proyecto/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 1.8 | 3 | 1.99
Defects/Hour - Code Review | 2.2 | 0 | 2
Defects/Hour - Compile | 0 | 0 | 0
Defects/Hour - Test | 2.56 | 0 | 2.35
DRL (DLDR/UT) | 0.7 | 1.27 | 0.84
DRL (Code Review/UT) | 0.86 | 0 | 0.85
DRL (Compile/UT) | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:23 PM el 18/04/2017